## Step-by-Step Checklist
🎓 School Management System — Learning & Development Checklist
Full-Stack Project: C++ Backend (REST API) + Supabase (Cloud PostgreSQL) + React Frontend (Vite)
Total Tasks | Not Started | In Progress | Completed | High Priority | Medium Priority | Optional | Completion %
Phase | Step ID | Task / Topic Name | Description & Key Learning Objectives | Tech & Libraries | Priority | Status | My Notes / Questions
Phase 1: Setup & Tools | 1.1 | C++ Compiler & Build System Setup | Verify GCC (MinGW) / compiler. Understand C++ compilation, linking, WinSock2, and include paths. | GCC, WinSock2 / C++14 | High | Completed | Verified working with C++14 & WinSock2 on current GCC!
Phase 1: Setup & Tools | 1.2 | Supabase Account & Project Creation | Create Supabase project. Obtain PostgreSQL direct/pooler URI, API URL, Anon Key, and Service Role Key. | Supabase Cloud, PostgreSQL | High | Completed | Project initialized: xzmirtkasmtuadvyslri & .env created!
Phase 1: Setup & Tools | 1.3 | C++ PostgreSQL / Supabase Connector Setup | Setup WinINet HTTPS SSL connection to Supabase PostgREST in C++. | WinINet / SSL / C++14 | High | Completed | C++ DatabaseClient tested & fetching live Supabase data!
Phase 1: Setup & Tools | 1.4 | C++ HTTP Server & REST API Setup | Build multi-client WinSock2 HTTP server with CORS and JSON routing on port 8080. | WinSock2, C++14 | High | Completed | C++ REST API Server live on http://127.0.0.1:8080!
Phase 1: Setup & Tools | 1.5 | React + Vite Project Initialization | Create modern React single-page app using Vite (`npm create vite@latest frontend`). | Node.js, React, Vite | High | Completed | React + Vite frontend scaffolded & dependencies installed!
Phase 2: Database Design (Supabase) | 2.1 | Core Entity-Relationship (ER) Architecture | Design schema: students, teachers, classes, subjects, attendance, grades. | Database Modeling, ER Diagrams | High | Completed | Executed Core DDL in Supabase!
Phase 2: Database Design (Supabase) | 2.2 | Student Fees & Receipt Schema | Create student_fees table with gross amount, discounts, fines, net payable, balance, receipt_no. | PostgreSQL DDL / Constraints | High | Completed | Created student_fees table in Supabase!
Phase 2: Database Design (Supabase) | 2.3 | Teacher Salary & Pay-Slip Schema | Create teacher_salaries table with basic, HRA, DA, PF, TDS, unpaid leaves, net salary, payslip_no. | PostgreSQL DDL / Constraints | High | Completed | Created teacher_salaries table in Supabase!
Phase 2: Database Design (Supabase) | 2.4 | Seed Realistic Test Data | Insert sample records for students, teachers, fee receipts, and teacher salary slips in Supabase. | PostgreSQL DML / Supabase | High | Completed | Seeded demo data successfully!
Phase 2: Database Design (Supabase) | 2.5 | Row-Level Security (RLS) & Policies | Understand Supabase RLS security model and configure policies for read/write access. | Supabase RLS & Security | Medium | Completed | Configured direct access for backend API!
Phase 3: C++ Backend DAO | 3.1 | Configuration & Environment Management | Create .env reader or config module in C++ to securely load Supabase credentials without hardcoding. | C++ Config / Env | High | Completed | Built config.h loading .env credentials dynamically!
Phase 3: C++ Backend DAO | 3.2 | C++ Domain Models (Structs/Classes) | Define C++ models: Student, Teacher, ClassSection, FeeReceipt, TeacherSalarySlip, Attendance, Grade. | C++14 Structs / Classes | High | Completed | Defined all domain structs in models.h!
Phase 3: C++ Backend DAO | 3.3 | Supabase HTTPS Connection Client | Implement a robust DB Connection Manager in C++ using WinINet HTTPS with SSL. | WinINet / C++ Client | High | Completed | Implemented db_client.cpp connecting to Supabase!
Phase 3: C++ Backend DAO | 3.4 | Parameterized Prepared Queries | Implement safe parameterized URL queries in C++ to eliminate SQL Injection risks. | SQL Security / URL Encoding | High | Completed | Tested parameterized PostgREST calls!
Phase 3: C++ Backend DAO | 3.5 | Student & Teacher DAO (Full CRUD) | Implement getAllStudents(), getStudentById(), addStudent(), updateStudent(), deleteStudent(). | C++ DAO Pattern | High | Completed | Built full student & teacher DAO methods!
Phase 3: C++ Backend DAO | 3.6 | Fee Receipt & Collection DAO | Implement recordFeePayment(), getStudentReceipts(), getPendingFees(), generateReceiptNo(). | C++ Business Logic / DAO | High | Completed | Built fee receipts and collection DAO!
Phase 3: C++ Backend DAO | 3.7 | Teacher Payroll & Salary Slip DAO | Implement generateSalarySlip(), getTeacherPaySlips(), computeSalaryCalculations(). | C++ Business Logic / DAO | High | Completed | Built salary pay-slips and payroll DAO!
Phase 3: C++ Backend DAO | 3.8 | Attendance & Gradebook Logic | Write queries to batch-mark attendance and compute student GPA / term averages. | C++ Business Logic | High | Completed | Built attendance & grades DAO methods!
Phase 3: C++ Backend DAO | 3.9 | C++ DAO Verification Test | Test executable against live Supabase PostgreSQL tables. | C++ Testing / CLI | Medium | Completed | Verified live data fetching from Supabase!
Phase 4: C++ REST API | 4.1 | HTTP Server Lifecycle & Port Listener | Initialize multi-client WinSock2 HTTP server listening on port 8080. Handle server shutdown cleanly. | WinSock2 Server | High | Completed | Built http_server.cpp listening on port 8080!
Phase 4: C++ REST API | 4.2 | CORS Middleware (Cross-Origin Resource Sharing) | Configure OPTIONS pre-flight handler and Access-Control-Allow-* headers for React frontend. | HTTP CORS Protocols | High | Completed | Enabled full CORS headers for React frontend!
Phase 4: C++ REST API | 4.3 | JSON Serialization & Deserialization | Format JSON responses and parse request payloads. | JSON / C++ | High | Completed | Built JSON request parser & response builder!
Phase 4: C++ REST API | 4.4 | Student & Teacher REST Endpoints | Build `GET/POST/PUT/DELETE /api/students` and `GET/POST/PUT/DELETE /api/teachers`. | REST API Design | High | Completed | Built /api/students & /api/teachers routes!
Phase 4: C++ REST API | 4.5 | Fee Management REST Endpoints | Build `GET /api/fees`, `POST /api/fees/collect`, `GET /api/fees/receipt/:receipt_no`. | REST API Design | High | Completed | Built /api/fees endpoints!
Phase 4: C++ REST API | 4.6 | Teacher Payroll REST Endpoints | Build `GET /api/salaries`, `POST /api/salaries/generate`, `GET /api/salaries/payslip/:id`. | REST API Design | High | Completed | Built /api/salaries endpoints!
Phase 4: C++ REST API | 4.7 | Attendance & Grades REST Endpoints | Build `GET/POST /api/attendance` and `GET/POST /api/grades` endpoints. | REST API Design | High | Completed | Built /api/attendance & /api/grades endpoints!
Phase 4: C++ REST API | 4.8 | Standardized Error Responses & HTTP Statuses | Ensure 200 OK, 201 Created, 400 Bad Request, 404 Not Found formatted as JSON. | HTTP Error Standards | Medium | Completed | Configured standardized HTTP responses!
Phase 5: React Frontend | 5.1 | Design System, Navigation & Layout | Create modern dark/light responsive layout: Sidebar, Header, Breadcrumbs, and content viewport. | React, CSS Grid / Flexbox | High | Completed | Built glassmorphism sidebar, tabs, and layout!
Phase 5: React Frontend | 5.2 | API Client Service Module (`api.js`) | Build centralized API service using Fetch with baseURL, error parsing, and JSON support. | Fetch API / REST | High | Completed | Centralized API service in api.js with robust error parsing!
Phase 5: React Frontend | 5.3 | Dashboard Metrics & Statistics Page | Create KPI overview cards (Total Students, Total Fees Collected, Salaries Paid). | React Hooks (useState, useEffect) | High | Completed | Live KPI metrics updating in real time!
Phase 5: React Frontend | 5.4 | Student Directory & Management Modal | Data table with real-time search, filter by class, Add Student Modal with validation, and Delete. | React Components, Controlled Forms | High | Completed | Full directory with live search and delete!
Phase 5: React Frontend | 5.5 | Teacher Management Page | Faculty profile cards, subject assignments, and add/edit teacher directory. | React Components | Medium | Completed | Faculty directory live with Supabase sync!
Phase 5: React Frontend | 5.6 | Student Fee Collection & Receipt Generator | Fee payment collection modal, live calculation of discount/fines, and printable official receipt slip. | React Components / PDF Print | High | Completed | Printable fee receipt slips working!
Phase 5: React Frontend | 5.7 | Teacher Payroll & Salary Slip Generator | Monthly salary generation matrix, earnings vs deductions calculation, and printable salary pay-slip. | React Components / PDF Print | High | Completed | Printable salary pay-slips working!
Phase 5: React Frontend | 5.8 | Attendance Roll-Call Tracker | Daily student attendance marking checklist with batch toggle (Present/Absent/Late) and save. | React State Management | High | Completed | Attendance tracker module live!
Phase 5: React Frontend | 5.9 | Grades & Report Card Viewer | Subject marks entry form, calculated percentages/grades, and printable student report card. | React Components | High | Completed | Gradebook module live!
Phase 5: React Frontend | 5.10 | Excel Database Studio & Multi-Sheet Manager | Create multi-sheet workbooks, export DB to Excel, and bulk import 100+ to thousands of rows into Supabase with upsert. | xlsx, Supabase PostgREST Upsert | High | Completed | Bulk upload & multi-sheet manager live!
Phase 6: Integration & Polish | 6.1 | End-to-End Integration Testing | Test complete lifecycle: React UI -> C++ REST API -> Supabase PostgreSQL DB -> Instant UI refresh. | E2E Testing & Verification | High | Completed | All 103+ records live and syncing across Dashboard & Directory!
Phase 6: Integration & Polish | 6.2 | Input Validation & Latency Handling | Form validation on frontend & backend (prevent duplicate roll numbers, empty names, invalid emails). | Data Integrity & Validation | Medium | Completed | Upsert resolution merge-duplicates enabled on all entities!
Phase 6: Integration & Polish | 6.3 | Optional: Supabase Auth / Role-based Access | Implement login screen for Admin vs Teacher vs Student with JWT authentication. | Supabase Auth / JWT | Optional | Not Started
Phase 6: Integration & Polish | 6.4 | Optional: Export to CSV / PDF | Export student fee ledger and teacher payroll summaries as CSV or printable PDF documents. | File Exporting | Optional | Completed | Multi-sheet Excel export active in Excel Studio!

## Architecture & Tech Stack
🏛️ System Architecture & Technology Breakdown
1. Full-Stack Layer Specification
Layer | Technology / Library | Role in System | Key Learning Takeaways
Frontend UI | React (Vite) + CSS3 | Modern responsive Single Page App | Component structure, state hooks, props, responsive dashboards
API Client | Fetch API / Axios | HTTP client calling C++ backend | Asynchronous promises, error interceptors, headers, CORS handling
Backend Core | C++ (C++14 / C++17) | High-performance business logic & controllers | Modern C++ memory management, smart pointers, structs, DAO pattern
HTTP Web Server | cpp-httplib / WinSock2 | Lightweight C++ REST API Server | HTTP routing, request dispatching, CORS headers, status codes
JSON Engine | nlohmann/json | JSON parsing & serialization | Modern C++ JSON manipulation, object serialization macros
Cloud Database | Supabase (PostgreSQL 15+) | Persistent relational storage in the cloud | Relational database modeling, SQL DDL/DML, Foreign Keys, RLS
Receipt & Slip Engine | React Printable Slips | Generate printable fee receipts and salary slips | CSS @media print styling, calculated financial breakdowns
2. Complete Database Table Blueprint (All 8 Tables)
Table Name | Primary Key | Foreign Keys | Key Columns | Description
students | id (BIGSERIAL PK) | class_id -> classes(id) | roll_number (UNIQUE), first_name, last_name, email, phone, dob, created_at | Student profiles and academic registration
teachers | id (BIGSERIAL PK) | None | employee_id (UNIQUE), first_name, last_name, email, phone, qualification, created_at | Faculty and staff details
classes | id (BIGSERIAL PK) | teacher_id -> teachers(id) | class_name, section, academic_year | Classroom divisions (e.g. Grade 10 - Section A)
subjects | id (BIGSERIAL PK) | None | subject_code (UNIQUE), subject_name, credits | Courses taught in curriculum
attendance | id (BIGSERIAL PK) | student_id -> students(id) | date, status ('Present', 'Absent', 'Late'), remarks, created_at | Daily attendance roll-call records
grades | id (BIGSERIAL PK) | student_id -> students(id), subject_id -> subjects(id) | exam_term ('Midterm', 'Final'), marks_obtained, max_marks, remarks | Subject examination marks and GPA records
student_fees | id (BIGSERIAL PK) | student_id -> students(id) | receipt_no (UNIQUE), gross_amount, discount_amount, late_fine, net_payable, amount_paid, balance_due, payment_status, payment_method | Fee collection records and printable receipt generation
teacher_salaries | id (BIGSERIAL PK) | teacher_id -> teachers(id) | payslip_no (UNIQUE), salary_month, salary_year, basic_salary, hra, da, pf, tds, leave_deduction, gross_earnings, total_deductions, net_salary | Payroll management and monthly teacher pay-slips

## Fees & Salaries (Slips)
💵 Student Fee Receipts & Teacher Salary Pay-Slips Blueprint
1. Student Fee Slip / Receipt Data Structure
Field Name | Data Type | Role in Receipt Generation | Example Receipt Value
receipt_no | VARCHAR(50) UNIQUE | Official Receipt Reference ID printed at top of slip | REC-2026-00101
student_id | BIGINT FK -> students(id) | Fetches Student Name, Roll No, Class, and Parent details | 1 (Alex Johnson - Grade 10A)
academic_year & term_name | VARCHAR(20), VARCHAR(50) | Academic session and fee period | 2026-2027 / Term 1
fee_category | VARCHAR(50) | Head of Account / Purpose | Tuition & Laboratory Fee
gross_amount | NUMERIC(10,2) | Base fee amount before discounts or penalties | ₹ 30,000.00
discount_amount | NUMERIC(10,2) | Scholarship / sibling concession deducted | ₹ 2,000.00
late_fine | NUMERIC(10,2) | Late fee penalty added if paid after due date | ₹ 0.00
net_payable | NUMERIC(10,2) | Formula: (gross_amount - discount_amount + late_fine) | ₹ 28,000.00
amount_paid | NUMERIC(10,2) | Amount actually received from student/parent | ₹ 28,000.00
balance_due | NUMERIC(10,2) | Formula: (net_payable - amount_paid) | ₹ 0.00 (Fully Settled)
payment_status | VARCHAR(20) | Status indicator on receipt ('Paid', 'Partial', 'Overdue') | Paid
payment_method & transaction_ref | VARCHAR(50), VARCHAR(100) | Mode of payment (UPI/Card/Cash) & Bank reference | UPI / QR (Ref: UPI/20260901/7839210)
received_by & payment_date | VARCHAR(100), TIMESTAMP | Cashier/Admin signature line & payment timestamp | Finance Desk 1 / Sep 05, 2026 11:30 AM
2. Teacher Salary Pay-Slip Data Structure
Field Name | Data Type | Role in Pay-Slip Generation | Example Pay-Slip Value
payslip_no | VARCHAR(50) UNIQUE | Official Pay-Slip Reference ID printed on top right | PAY-2026-AUG-01
teacher_id | BIGINT FK -> teachers(id) | Fetches Teacher Name, Employee ID, Subject & Designation | 1 (Robert Miller - Mathematics)
salary_month & salary_year | VARCHAR(20), INT | Salary pay period | August 2026
working_days & leaves_taken | INT, INT | Attendance section: Working days vs Present vs Unpaid Leaves | 31 Days Worked / 0 Leaves
basic_salary (Earnings) | NUMERIC(10,2) | Base contract salary | ₹ 45,000.00
hra_allowance (Earnings) | NUMERIC(10,2) | House Rent Allowance | ₹ 12,000.00
da_allowance (Earnings) | NUMERIC(10,2) | Dearness Allowance | ₹ 8,000.00
medical & special_bonus (Earnings) | NUMERIC(10,2) | Medical allowance and performance bonus | ₹ 3,000.00 + ₹ 2,000.00
gross_earnings | NUMERIC(10,2) | Total Gross Earnings = Basic + HRA + DA + Medical + Bonus | ₹ 70,000.00
provident_fund (Deductions) | NUMERIC(10,2) | PF retirement contribution deduction | ₹ 4,000.00
tax_deducted_tds (Deductions) | NUMERIC(10,2) | Income Tax TDS deduction | ₹ 2,500.00
leave_deduction (Deductions) | NUMERIC(10,2) | Salary deducted for unpaid absence | ₹ 0.00
total_deductions | NUMERIC(10,2) | Total Deductions = PF + TDS + Leave Deductions | ₹ 6,500.00
net_salary | NUMERIC(10,2) | Net Take-Home Pay = (Gross Earnings - Total Deductions) | ₹ 63,500.00
payment_method & bank_account_last4 | VARCHAR(50), VARCHAR(10) | Bank transfer method & masked account number | Direct Bank Transfer (A/C: XXXX-5678)
transaction_ref & payment_date | VARCHAR(100), TIMESTAMP | Bank NEFT/RTGS transaction ID & payment timestamp | NEFT-HDFC-99887711 / Aug 31, 2026

## Supabase SQL Scripts
⚡ Complete Executable SQL Scripts for Supabase SQL Editor
Section | SQL DDL & DML Code (Run in Supabase Dashboard -> SQL Editor)
1. Core Tables DDL (Teachers, Classes, Students, Subjects, Attendance, Grades) | -- 1. Create Teachers Table CREATE TABLE IF NOT EXISTS teachers ( id BIGSERIAL PRIMARY KEY, employee_id VARCHAR(50) UNIQUE NOT NULL, first_name VARCHAR(100) NOT NULL, last_name VARCHAR(100) NOT NULL, email VARCHAR(150) UNIQUE NOT NULL, phone VARCHAR(20), qualification VARCHAR(100), created_at TIMESTAMP WITH TIME ZONE DEFAULT NOW() ); -- 2. Create Classes Table CREATE TABLE IF NOT EXISTS classes ( id BIGSERIAL PRIMARY KEY, class_name VARCHAR(50) NOT NULL, section VARCHAR(10) NOT NULL, teacher_id BIGINT REFERENCES teachers(id) ON DELETE SET NULL, academic_year VARCHAR(20) NOT NULL DEFAULT '2026-2027', created_at TIMESTAMP WITH TIME ZONE DEFAULT NOW(), UNIQUE(class_name, section, academic_year) ); -- 3. Create Students Table CREATE TABLE IF NOT EXISTS students ( id BIGSERIAL PRIMARY KEY, roll_number VARCHAR(50) UNIQUE NOT NULL, first_name VARCHAR(100) NOT NULL, last_name VARCHAR(100) NOT NULL, email VARCHAR(150) UNIQUE NOT NULL, phone VARCHAR(20), dob DATE, class_id BIGINT REFERENCES classes(id) ON DELETE SET NULL, enrollment_date DATE DEFAULT CURRENT_DATE, created_at TIMESTAMP WITH TIME ZONE DEFAULT NOW() ); -- 4. Create Subjects Table CREATE TABLE IF NOT EXISTS subjects ( id BIGSERIAL PRIMARY KEY, subject_code VARCHAR(20) UNIQUE NOT NULL, subject_name VARCHAR(100) NOT NULL, credits INT DEFAULT 3 ); -- 5. Create Attendance Table CREATE TABLE IF NOT EXISTS attendance ( id BIGSERIAL PRIMARY KEY, student_id BIGINT NOT NULL REFERENCES students(id) ON DELETE CASCADE, date DATE NOT NULL DEFAULT CURRENT_DATE, status VARCHAR(20) CHECK (status IN ('Present', 'Absent', 'Late')), remarks VARCHAR(255), created_at TIMESTAMP WITH TIME ZONE DEFAULT NOW(), UNIQUE(student_id, date) ); -- 6. Create Grades Table CREATE TABLE IF NOT EXISTS grades ( id BIGSERIAL PRIMARY KEY, student_id BIGINT NOT NULL REFERENCES students(id) ON DELETE CASCADE, subject_id BIGINT NOT NULL REFERENCES subjects(id) ON DELETE CASCADE, exam_term VARCHAR(50) NOT NULL, marks_obtained NUMERIC(5,2) NOT NULL, max_marks NUMERIC(5,2) NOT NULL DEFAULT 100.00, remarks VARCHAR(255), created_at TIMESTAMP WITH TIME ZONE DEFAULT NOW() );
2. Fees & Salary Slips DDL (student_fees, teacher_salaries) | -- 7. Create Student Fee Receipts Table CREATE TABLE IF NOT EXISTS student_fees ( id BIGSERIAL PRIMARY KEY, receipt_no VARCHAR(50) UNIQUE NOT NULL, student_id BIGINT NOT NULL REFERENCES students(id) ON DELETE CASCADE, academic_year VARCHAR(20) NOT NULL DEFAULT '2026-2027', term_name VARCHAR(50) NOT NULL DEFAULT 'Term 1', fee_category VARCHAR(50) NOT NULL, gross_amount NUMERIC(10,2) NOT NULL, discount_amount NUMERIC(10,2) DEFAULT 0.00, late_fine NUMERIC(10,2) DEFAULT 0.00, net_payable NUMERIC(10,2) NOT NULL, amount_paid NUMERIC(10,2) NOT NULL DEFAULT 0.00, balance_due NUMERIC(10,2) NOT NULL, payment_status VARCHAR(20) CHECK (payment_status IN ('Paid', 'Partial', 'Pending', 'Overdue')) DEFAULT 'Pending', payment_method VARCHAR(50), transaction_ref VARCHAR(100), due_date DATE NOT NULL, payment_date TIMESTAMP WITH TIME ZONE, received_by VARCHAR(100) DEFAULT 'Admin Office', notes VARCHAR(255), created_at TIMESTAMP WITH TIME ZONE DEFAULT NOW() ); -- 8. Create Teacher Salary Pay-Slips Table CREATE TABLE IF NOT EXISTS teacher_salaries ( id BIGSERIAL PRIMARY KEY, payslip_no VARCHAR(50) UNIQUE NOT NULL, teacher_id BIGINT NOT NULL REFERENCES teachers(id) ON DELETE CASCADE, salary_month VARCHAR(20) NOT NULL, salary_year INT NOT NULL DEFAULT 2026, total_working_days INT NOT NULL DEFAULT 30, days_present INT NOT NULL DEFAULT 30, leaves_taken INT NOT NULL DEFAULT 0, basic_salary NUMERIC(10,2) NOT NULL, hra_allowance NUMERIC(10,2) DEFAULT 0.00, da_allowance NUMERIC(10,2) DEFAULT 0.00, medical_allowance NUMERIC(10,2) DEFAULT 0.00, special_bonus NUMERIC(10,2) DEFAULT 0.00, gross_earnings NUMERIC(10,2) NOT NULL, provident_fund NUMERIC(10,2) DEFAULT 0.00, tax_deducted_tds NUMERIC(10,2) DEFAULT 0.00, leave_deduction NUMERIC(10,2) DEFAULT 0.00, total_deductions NUMERIC(10,2) NOT NULL, net_salary NUMERIC(10,2) NOT NULL, payment_status VARCHAR(20) CHECK (payment_status IN ('Paid', 'Pending', 'Processing')) DEFAULT 'Pending', payment_method VARCHAR(50) DEFAULT 'Direct Bank Transfer', bank_account_last4 VARCHAR(10), payment_date TIMESTAMP WITH TIME ZONE, transaction_ref VARCHAR(100), created_at TIMESTAMP WITH TIME ZONE DEFAULT NOW(), UNIQUE(teacher_id, salary_month, salary_year) );
3. Seed Demo Data (Students, Teachers, Classes, Fees, Salaries) | -- Seed Sample Teachers & Classes INSERT INTO teachers (employee_id, first_name, last_name, email, phone, qualification) VALUES ('TCH-001', 'Robert', 'Miller', 'robert.miller@school.edu', '555-0101', 'M.Sc. Mathematics'), ('TCH-002', 'Sarah', 'Connor', 'sarah.connor@school.edu', '555-0102', 'Ph.D. Physics'), ('TCH-003', 'Emily', 'Davis', 'emily.davis@school.edu', '555-0103', 'M.A. English') ON CONFLICT (employee_id) DO NOTHING; INSERT INTO classes (class_name, section, teacher_id, academic_year) VALUES ('Grade 10', 'A', 1, '2026-2027'), ('Grade 10', 'B', 2, '2026-2027'), ('Grade 11', 'A', 3, '2026-2027') ON CONFLICT (class_name, section, academic_year) DO NOTHING; -- Seed Sample Students INSERT INTO students (roll_number, first_name, last_name, email, phone, dob, class_id) VALUES ('STU-1001', 'Alex', 'Johnson', 'alex.j@student.edu', '555-1101', '2008-04-12', 1), ('STU-1002', 'Sophia', 'Williams', 'sophia.w@student.edu', '555-1102', '2008-09-21', 1), ('STU-1003', 'Liam', 'Brown', 'liam.b@student.edu', '555-1103', '2008-01-15', 2), ('STU-1004', 'Emma', 'Jones', 'emma.j@student.edu', '555-1104', '2008-07-30', 2) ON CONFLICT (roll_number) DO NOTHING; -- Seed Sample Fee Receipts INSERT INTO student_fees (receipt_no, student_id, academic_year, term_name, fee_category, gross_amount, discount_amount, late_fine, net_payable, amount_paid, balance_due, payment_status, payment_method, transaction_ref, due_date, payment_date, received_by) VALUES ('REC-2026-001', 1, '2026-2027', 'Term 1', 'Tuition & Lab Fee', 30000.00, 2000.00, 0.00, 28000.00, 28000.00, 0.00, 'Paid', 'UPI / QR', 'UPI/20260901/7839210', '2026-09-10', '2026-09-05 11:30:00+00', 'Finance Desk 1'), ('REC-2026-002', 2, '2026-2027', 'Term 1', 'Tuition & Lab Fee', 30000.00, 0.00, 0.00, 30000.00, 15000.00, 15000.00, 'Partial', 'Debit/Credit Card', 'CARD-TXN-99881', '2026-09-10', '2026-09-08 14:15:00+00', 'Finance Desk 2'), ('REC-2026-003', 3, '2026-2027', 'Term 1', 'Tuition & Transport', 35000.00, 0.00, 500.00, 35500.00, 0.00, 35500.00, 'Overdue', NULL, NULL, '2026-09-01', NULL, 'Finance Desk 1') ON CONFLICT (receipt_no) DO NOTHING; -- Seed Sample Teacher Salary Pay-Slips INSERT INTO teacher_salaries (payslip_no, teacher_id, salary_month, salary_year, total_working_days, days_present, leaves_taken, basic_salary, hra_allowance, da_allowance, medical_allowance, special_bonus, gross_earnings, provident_fund, tax_deducted_tds, leave_deduction, total_deductions, net_salary, payment_status, payment_method, bank_account_last4, payment_date, transaction_ref) VALUES ('PAY-2026-AUG-01', 1, 'August', 2026, 31, 31, 0, 45000.00, 12000.00, 8000.00, 3000.00, 2000.00, 70000.00, 4000.00, 2500.00, 0.00, 6500.00, 63500.00, 'Paid', 'Direct Bank Transfer', '5678', '2026-08-31 10:00:00+00', 'NEFT-HDFC-99887711'), ('PAY-2026-AUG-02', 2, 'August', 2026, 31, 30, 1, 50000.00, 15000.00, 9000.00, 3000.00, 0.00, 77000.00, 4500.00, 3200.00, 1000.00, 8700.00, 68300.00, 'Paid', 'Direct Bank Transfer', '9012', '2026-08-31 10:00:00+00', 'NEFT-SBI-44556622') ON CONFLICT (teacher_id, salary_month, salary_year) DO NOTHING;

## Role-Based Auth & Access Plan
🔐 Role-Based Access Control (RBAC) & Multi-Role Authentication Plan
Secure Login System: Student Personal Portal • Teacher Evaluation & Payroll Portal • Admin Master Console
Total User Roles | Student Portal Scope | Teacher Portal Scope | Admin Console Scope | Security Model | Status
3 Distinct Roles | Own Fees, Grades, Attendance & Timetable | Own Salary, Student Remarks (No Add/Remove) | Full System Master Control | Role-Based Token / Session RBAC | Planned & Ready
1. Role Permissions & Feature Access Matrix (RBAC)
Portal / User Role | Authentication Method | Permitted Features & Data Scope | Restricted / Forbidden Actions | Navigation Items Available | Database Data Security Filter
Student Portal (role: 'student') | Username / Roll Number + Password (FK: student_id) | • View own fee receipts & installment payment history • Check current outstanding fee balance • View own semester grades, report card & marks • Track personal daily attendance & percentage • View weekly class timetable & assigned subject faculty | • CANNOT view other students' records or fees • CANNOT modify, delete, or create any record • CANNOT view faculty payroll, salaries, or admissions • Strictly Read-Only personal dashboard | 1. My Overview / Profile 2. My Fee Receipts & Dues 3. My Grades & Report Card 4. My Attendance Records 5. Class Timetable & Teachers | WHERE student_id = :authenticated_student_id (Enforced at API and Database query level)
Faculty / Teacher Portal (role: 'teacher') | Employee ID / Email + Password (FK: teacher_id) | • View own monthly salary pay-slips & annual payroll ledger • View assigned students directory (roll no, name, class) • Enter & update student progress remarks / feedback • View personal teaching schedule & assigned classes • Check student attendance in assigned classes | • CANNOT add, enroll, or remove/delete students • CANNOT modify student fees or collect payments • CANNOT view other teachers' salaries • CANNOT access Excel Database Studio or system configs | 1. Faculty Dashboard 2. My Salary Pay-Slips 3. Assigned Students Directory 4. Student Progress Remarks 5. My Teaching Schedule | WHERE teacher_id = :authenticated_teacher_id (for salaries) WHERE class_id IN (teacher_classes) (for students)
Administrator Console (role: 'admin') | Admin Username / Email + Password (Superuser privileges) | • Complete master management across entire school • Student directory: Add, edit, bulk import, delete • Faculty directory: Add, manage, assign classes • Fee collection: Multi-installment receipts & slips • Payroll processing: Disburse monthly faculty salaries • Excel Database Studio: 1-click bulk import & export | • No restrictions (Superuser / Management level access) | 1. Master Dashboard KPIs 2. Student Directory 3. Faculty & Staff 4. Fee Receipts & Installments 5. Faculty Payroll & Pay-Slips 6. Excel Database Studio | Full read/write access across all system tables without filter restriction
2. Database Schema for Authentication & RBAC Support
Table Name | Primary Key | Foreign Keys | Key Columns & Constraints | Role in RBAC System | Target Access Role
users (Central Auth) | id BIGSERIAL | student_id -> students(id) teacher_id -> teachers(id) | username (UNIQUE), email (UNIQUE), password_hash, role CHECK (role IN ('admin','teacher','student')), status ('active','inactive'), last_login_at | Master authentication store with hashed credentials and role assignment linking to student/teacher profile. | Admin / Teacher / Student (Login Entry)
student_progress_remarks (Evaluation) | id BIGSERIAL | student_id -> students(id) teacher_id -> teachers(id) | academic_term, subject_name, performance_level, remark_text TEXT NOT NULL, created_at | Allows teachers to write evaluation remarks for students without granting them add/delete permissions for students. | Teacher (Write/Read), Student (Read-Only)
student_grades_results (Academic Results) | id BIGSERIAL | student_id -> students(id) | subject_name, exam_type (Midterm/Final), marks_obtained, max_marks (100.00), grade (A+, A, B, etc.), academic_year | Stores course examination grades and terminal marks for student personal report card view. | Admin/Teacher (Manage), Student (Read-Only)
subject_teachers_timetable (Class Schedule) | id BIGSERIAL | class_id -> classes(id) teacher_id -> teachers(id) | subject_name, day_of_week (Monday..Friday), start_time, end_time, room_number | Connects subjects with teachers and class timings so students view assigned faculty and lecture schedule. | Admin (Manage), Teacher & Student (Read-Only)
3. Step-by-Step Execution Plan & Milestones
Step ID | Phase | Milestone / Implementation Task | Scope & Deliverables | Target Files | Priority
AUTH-01 | Database Migration | Create Auth & RBAC Tables in Supabase | Run SQL DDL for users, student_progress_remarks, student_grades, subject_teachers_timetable | Supabase SQL Editor / models.h | High
AUTH-02 | Data Seeding | Seed Default Role Accounts & Test Credentials | Create Admin account, 3 Teacher accounts (TCH-001..003), and 3 Student accounts (STU-1001..1005) | SQL Seed Script / Checklist | High
AUTH-03 | Backend Core | Implement C++ Login REST Endpoint | Add POST /api/auth/login validating username/password and returning user role, token & profile ID | backend/src/http_server.cpp | High
AUTH-04 | Frontend UI | Build Authentication Login Screen & Demo Switcher | Glassmorphism Login page with role switcher tabs (Student / Teacher / Admin) and 1-click test fill | frontend/src/Login.jsx | High
AUTH-05 | Frontend Security | Implement Session State & Navigation Guard | Store active session in React state/localStorage with Logout button and role-aware navigation bar | frontend/src/App.jsx | High
AUTH-06 | Student Portal | Build Student Personal Dashboard & My Records | Student views own fees & installments, grades/results, attendance, lecture schedule & subject faculty | frontend/src/StudentPortal.jsx | High
AUTH-07 | Teacher Portal | Build Teacher Portal & Student Remarks System | Teacher views own salary pay-slips, assigned student directory (read-only), adds academic remarks | frontend/src/TeacherPortal.jsx | High
AUTH-08 | Verification | End-to-End Testing & Visual Audit | Verify login across all 3 roles, test permission boundaries, capture visual snapshot 'snap1' | All Components & Walkthrough | High